## TIMELINE PRODUCTION
TIMELINE PRODUKSI
| Project | : XL FAREWELL
| Location | : KASABLANKA HAL
| Tanggal Loading | : 19-20 Desember 2024
| Tanggal event | : 21 Desember 2024
NO | ITEM | MARET
|  | 15 | 16 | 17 | 18 | 19
1 | Orchestra Level
2 | Exstension Stage
3 | Tunnel Gate
4 | Partisi Gate

## TIMELINE LOADING
TIMELINE LOADING
| Project | [19 empty] | : XL FAREWELL
| Location | [19 empty] | : KASABLANKA HAL
| Tanggal Loading | [19 empty] | : 19-20 Desember 2024
| Tanggal event | [19 empty] | : 21 Desember 2024
NO | ITEM | 2025-03-18 | [6 empty] | 2025-03-19 | [22 empty] | 2025-03-20 | [23 empty] | 2025-03-21
|  | 18.00 | 19.00 | 20.00 | 21.00 | 22.00 | 23.00 | 00.00 | 01.00 | 02.00 | 03.00 | 04.00 | 05.00 | 06.00 | 07.00 | 08.00 | 09.00 | 10.00 | 11.00 | 12.00 | 13.00 | 14.00 | 15.00 | 16.00 | 17.00 | 18.00 | 19.00 | 20.00 | 21.00 | 22.00 | 23.00 | 00.00 | 01.00 | 02.00 | 03.00 | 04.00 | 05.00 | 06.00 | 07.00 | 08.00 | 09.00 | 10.00 | 11.00 | 12.00 | 13.00 | 14.00 | 15.00 | 16.00 | 17.00 | 18.00 | 19.00 | 20.00 | 21.00 | 22.00 | 23.00 | 00.00 | 01.00 | 02.00 | 03.00
1 | Load-In Preparation | [23 empty] | B R E A K | [6 empty] | B R E A K |  |  |  | B R E A K | [13 empty] | B R E A K
2 | Mobilisasi
3 | Load-In Construction
4 | Orchestra Level & Cover Stage Trapesium
5 | Exstension Stage
6 | Pathway Motorcycle
7 | Cover FOH
8 | Tunnel Gate
9 | LED Tunnel
10 | Partisi Gate
11 | Finishing All Item
12 | Clear Area

## CHECKLIST FA
CHECKLIST FA
No | ITEM | QTY | MATERIAL Fin. | LINK | STATUS
1 | GATE
| - Logo Harmony Of Gratitude | 1 |  | click here | Approved
| - Logo XL Axiata | 1 |  | click here | Approved
| - Flexi Backdrop Kanan Kiri | 2 | Flexi | click here | Approved

## CHECKLIST PRODUCTION
TYPE | : | CUSTOM PRODUCTION
NO | DESCRIPTION |  | REMARKS | DETAIL SPEC | QTY |  | DUR |  | FREQ |  | PIC
A | BALLROOM
1 | LEVEL ORCHESTRA
| - | Modul 14.64 x 1.83 x 0.2 m |  | Plywood Module | 1 | set | 1 | day/s | 1 | event
| - | Finishing Karpet Buana 14.64 x 1.83 x 0.2 m |  | Black | 1 | set | 1 | day/s | 1 | event
| - | Modul 14.64 x 1.83 x 0.4 m |  | Plywood Module | 1 | set | 1 | day/s | 1 | event
| - | Finishing Karpet Buana 14.64 x 1.83 x 0.4 m |  | Black | 1 | set | 1 | day/s | 1 | event
2 | COVER STAGE
| - | Black Carpet 14.64 x 3.72 m |  | Trapezion Shape | 1 | set | 1 | day/s | 1 | event
3 | EXTENSION STAGE
| - | Modul 19.5 x 4.8 x 0.6 m |  | Hollow Steel Module | 1 | set | 1 | day/s | 1 | event
| - | Finishing Karpet Buana 19.5 x 4.8 x 0.6 m |  | Black | 1 | set | 1 | day/s | 1 | event
| - | Tangga R L 4.8 x 0.6 x 0.4 m |  |  | 2 | unit | 1 | day/s | 1 | event
| - | Finishing Karpet Buana 4.8 x 0.6 x 0.4 m |  | Black | 2 | unit | 1 | day/s | 1 | event
| - | Tangga Stage 4.8 x 0.6 x 0.4 m |  |  | 1 | unit | 1 | day/s | 1 | event
| - | Finishing Karpet Buana 4.8 x 0.6 x 0.4 m |  | Black | 1 | unit | 1 | day/s | 1 | event
| - | Tangga Center Stage 4.8 x 0.6 x 0.4 m |  |  | 1 | unit | 1 | day/s | 1 | event
| - | Finishing Karpet Buana 4.8 x 0.6 x 0.4 m |  | Black | 1 | unit | 1 | day/s | 1 | event
4 | PATHWAY MOTORCYCLE
| - | Modul 2.44 x 25 m |  |  | 1 | set | 1 | day/s | 1 | event
| - | Finishing Black Carpet |  |  | 1 | set | 1 | day/s | 1 | event
B | FOYER
1 | GATE TUNNEL
| a | Fascia
| - | Fascia Custom 6 x 3.5 m |  |  | 1 | set | 1 | day/s | 1 | event | KASABLANKA HALL
| - | Finishing Emulsion Paint |  |  | 1 | set | 1 | day/s | 1 | event
| - | Downlight fin. Sticker |  |  | 1 | set | 1 | day/s | 1 | event
| - | List Lighted |  |  | 1 | set | 1 | day/s | 1 | event
| - | Blue Velvet Fabric; Front and Rear Tunnel |  |  | 1 | set | 1 | day/s | 1 | event
| - | Logo XL Axiata |  |  | 1 | set | 1 | day/s | 1 | event
| - | Akrilik Lighted Finishing Sticker |  |  | 1 | set | 1 | day/s | 1 | event
| - | Logo XL Harmony Of Gratitude |  |  | 1 | set | 1 | day/s | 1 | event
| - | Akrilik Finishing Lighted |  |  | 1 | set | 1 | day/s | 1 | event
| - | Support System |  | Cabling etc | 1 | pckg | 1 | day/s | 1 | event
| b | Tunnel
| - | Construction 4.8 x 4 x 3.5 m |  |  | 1 | set | 1 | day/s | 1 | event
| - | Finishing Samping Kain Hitam |  |  | 1 | set | 1 | day/s | 1 | event
| - | Finishing Atas Emulsion Paint |  |  | 1 | set | 1 | day/s | 1 | event
| - | Base LED |  |  | 1 | set | 1 | day/s | 1 | event
| c | Gate Partition
| - | Construction 4.5 x 3 m |  |  | 2 | set | 1 | day/s | 1 | event
| - | Finishing Flexi |  |  | 2 | set | 1 | day/s | 1 | event